## Slide 1: District Five Projects Update
Florida Department of TRANSPORTATION
November, 2014

## Slide 2
UNDER CONSTRUCTION
  #1 I-4 from SR 44 to I-95
  #2 I-95 from Brevard County to SR 44
  #3 I-95 Interchange @ I-4/US 92 and widening to SR 44
  #4 US 92 Pedestrian Safety Improvements
UPCOMING
I-95 Interchange @ Matanzas Woods Pkwy
I-4 Managed Lanes PD&E Study
November, 2014

## Slide 3
UNDER CONSTRUCTION
  #1 I-4
  from SR 44 to I-95
  #2 I-95
  from Brevard County to SR 44
  #3 I-95 Interchange @ I-4/US 92 and widening to SR 44
  #4 US 92 Pedestrian
  Safety Improvements

## Slide 4: Project #1 I-4 WIDENING From SR 44 TO I-95
Flyover from US 92 to I-4
I-4 at the Tomoka River

## Slide 5
On-going Construction Activities:
  Temporary pavement and shoulders for the next traffic phase
  Concrete paving
  Ramp and bridge from I-4 to US 92
Project #1 I-4 WIDENING From SR 44 TO I-95

## Slide 6
  Estimated project completion:
  May 2016
I-4 Corridor
Project #1 I-4 WIDENING From SR 44 TO I-95

## Slide 7
UNDER CONSTRUCTION
  #1 I-4
  from SR 44 to I-95
  #2 I-95
  from Brevard County to SR 44
  #3 I-95 Interchange @ I-4/US92 and widening to SR 44
  #4 US 92 Pedestrian
  Safety Improvements

## Slide 8
  Widening to Brevard/Volusia line complete
  early 2016.
  Widening from Brevard/Volusia line to SR 44 complete
  Spring 2016.
I-95 Corridor
Project #2
I-95 WIDENING From Brevard County to SR 44

## Slide 9
UNDER CONSTRUCTION
  #1 I-4
  from SR 44 to I-95
  #2 I-95
  from Brevard County to SR 44
  #3 I-95 Interchange @ I-4/US92 and widening to SR 44
  #4 US 92 Pedestrian
  Safety Improvements

## Slide 10: Project #3 I-95 INTERCHANGE @ I-4 / US 92 and widening to SR 44
I-95 & US 92 INTERCHANGE
I-95 & I-4 INTERCHANGE

## Slide 11
I-95 & I-4 INTERCHANGE
  Construction begins January 2015
  MOT phasing for events in Daytona
  Project complete late 2017
I-95 & US 92 INTERCHANGE
Project #3 I-95 Interchange @ I-4/US 92 and widening to SR 44

## Slide 12
UNDER CONSTRUCTION
  #1 I-4
  from SR 44 to I-95
  #2 I-95
  from Brevard County to SR 44
  #3 I-95 Interchange @ I-4/US92 and widening to SR 44
  #4 US 92 Pedestrian
  Safety Improvements

## Slide 13: Project #4 US 92 (ISB) PEDESTRIAN SAFETY IMPROVEMENTS from Williamson Blvd to Midway Ave
November 26, 2014

## Slide 14
Phasing Activities:
  Demucking
  Stormwater pipe installation
  Sidewalk
Scheduled Completion
Late 2015
Project #4 US 92 Pedestrian Safety

## Slide 15
I-4 Corridor
Work overseen by Flagler County
Construction starts
early spring of 2015
Expected completion
summer 2016
I-95 Interchange @ Mantanzas Woods Parkway
Mantanzas Woods
Interchange@ I-95

## Slide 16
I-4 Managed Lanes from Seminole County to SR 472

## Slide 17
Add ramp from I-4 to eastbound Debary Avenue
Preserve recently constructed trail
Relocate park and ride to the west side of I-4
Dirksen Drive/Debary Avenue
New Ramp
Relocated Park and Ride
I-4 Managed Lanes

## Slide 18
Saxon Boulevard
Widening of Saxon Blvd to Normandy Blvd
Ramp Improvements
Six Lanes
I-4 Managed Lanes

## Slide 19
Rhode Island Avenue Extension
New Park and Ride
Four Lanes
New Express Lane Interchange
Direct connect to Express lanes
Construct all 4 lanes
Park & Ride on east side
I-4 Managed Lanes

## Slide 20
SR 472
Diverging Diamond Interchange
Improvements at MLK and Graves
Intersection Improvements
Intersection Improvements
I-4 Managed Lanes

## Slide 21
Mainline I-4 Typical Section
Two Alternatives Developed
      Alt 1 – Without rail corridor
      Alt 2 – With transit corridor (PREFERRED ALTERNATIVE)
I-4 Managed Lanes

## Slide 22
Carry two lanes each direction to east of Dirksen and one lane each direction to past Rhode Island
Carry two lanes each direction all the way to Rhode Island
(PREFERRED ALTERNATIVE)
Express Lane Limits
I-4 Managed Lanes

## Slide 23
Option | Express Lanes |  | Rail | Homes Impacted |  | Businesses Impacted |  | Ponds (Acres) | Wetland Impacts (Acres) | Costs (Millions of Dollars) |  |  | 
 | County Line to Dirksen Drive | Dirksen Drive to Rhode Island |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Partial | Full | Partial | Full |  |  | Wetlands Mitigation | Right of Way | Construc tion | Total
1 | 2 | 2 | NO | 0 | 0 | 1 | 0 | 9.6 | 3.8 | 0.4 | 0.4 | 290 | 290.8
2 | 2 | 2 | YES | 2 | 24 | 3 | 1 | 13.5 | 13 | 1.5 | 10.1 | 308 | 319.6
3 | 2 | 1 | NO | 0 | 0 | 0 | 0 | 5.4 | 3.8 | 0.4 | 0.4 | 286 | 286.8
4 | 2 | 1 | YES | 0 | 24 | 0 | 0 | 9.3 | 13 | 1.5 | 10.1 | 294 | 305.6
DECISIONS
I-4 Managed Lanes

## Slide 24: District Five Projects Update
Florida Department of TRANSPORTATION
November, 2014